## NIST CSF Maturity
NIST Cybersecurity Framework 2.0 - Maturity Assessment
Organization: Sample Enterprise Inc. ¦ Assessment Date: March 2026 ¦ Assessor: Ayomipo Alademehin, CISA
Function / Category | Subcategory | Current | Target | Gap | Remediation Action | Priority
GOVERN (GV) | GV.OC: Organizational Context
| GV.OC-01: Cybersecurity roles defined | 2 | 4 | 2 | Formalize RACI matrix; define CISO/CIO responsibilities | High
| GV.OC-02: Internal & external stakeholders identified | 3 | 4 | 1 | Document stakeholder register with touchpoint mapping | Medium
GV.RM: Risk Management Strategy
| GV.RM-01: Risk management priorities established | 2 | 4 | 2 | Develop risk appetite statement; board approval required | Critical
| GV.RM-02: Risk tolerance determined | 1 | 3 | 2 | Quantify risk tolerance by asset category (FAIR model) | High
GV.SC: Cybersecurity Supply Chain
| GV.SC-01: Third-party risk management established | 2 | 4 | 2 | Implement TPRM program with vendor DDQ and tiering | High
IDENTIFY (ID) | ID.AM: Asset Management
| ID.AM-01: Physical devices inventoried | 3 | 4 | 1 | Deploy automated asset discovery tool (e.g., Qualys) | Medium
| ID.AM-02: Software platforms inventoried | 2 | 4 | 2 | Implement CMDB in ServiceNow; integrate with SIEM | High
ID.RA: Risk Assessment
| ID.RA-01: Asset vulnerabilities identified | 2 | 4 | 2 | Deploy vulnerability scanning (quarterly + ad-hoc) | High
| ID.RA-02: Cyber threat intelligence received | 1 | 3 | 2 | Subscribe to threat intel feeds (CISA, industry ISACs) | Medium
PROTECT (PR) | PR.AA: Identity & Access Management
| PR.AA-01: Identities authenticated | 3 | 4 | 1 | Enforce MFA for all privileged accounts | High
| PR.AA-02: Access permissions managed | 2 | 4 | 2 | Implement quarterly access reviews; automate deprovisioning | High
PR.DS: Data Security
| PR.DS-01: Data at rest protected | 3 | 4 | 1 | Enable encryption for databases and file shares | High
| PR.DS-02: Data in transit protected | 3 | 4 | 1 | Enforce TLS 1.2+ for all external connections | Medium
DETECT (DE) | DE.CM: Continuous Monitoring
| DE.CM-01: Networks monitored | 2 | 4 | 2 | Deploy SIEM (Splunk/Sentinel); tune alerting rules | Critical
| DE.CM-02: Physical environment monitored | 3 | 4 | 1 | Integrate badge access logs with SIEM | Low
DE.AE: Adverse Event Analysis
| DE.AE-01: Baselines established | 2 | 3 | 1 | Define network/user behavior baselines in SIEM | Medium
RESPOND (RS) | RS.MA: Incident Management
| RS.MA-01: Incident response executed | 2 | 4 | 2 | Formalize IR playbook per NIST SP 800-61 | Critical
| RS.MA-02: Incident reported | 3 | 4 | 1 | Train staff on incident reporting procedures | High
RS.CO: Incident Response Communications
| RS.CO-01: Personnel notified | 2 | 3 | 1 | Create escalation matrix and communication templates | Medium
RECOVER (RC) | RC.RP: Recovery Planning
| RC.RP-01: Recovery plan executed | 2 | 4 | 2 | Develop BCP/DRP with RTO/RPO for critical systems | High
| RC.RP-02: Recovery activities communicated | 2 | 3 | 1 | Document communication plan for recovery scenarios | Medium
Maturity Levels: 0 = Non-Existent ¦ 1 = Initial/Ad Hoc ¦ 2 = Repeatable ¦ 3 = Defined/Standardized ¦ 4 = Managed/Optimized

## Executive Summary
NIST CSF 2.0 Maturity Assessment - Executive Summary
Assessment Date: | March 22, 2026
Assessor: | Ayomipo H. Alademehin, CISA
Scope: | Enterprise-wide cybersecurity posture across all 6 NIST CSF functions
KEY FINDINGS:
Average Current Maturity: | 2.3 / 4.0 (Repeatable level with gaps)
Average Target Maturity: | 3.8 / 4.0 (Managed/Optimized)
Overall Gap: | 1.5 maturity levels
PRIORITY AREAS FOR INVESTMENT:
Critical (Immediate): | 3 gaps - Risk appetite definition, SIEM deployment, IR playbook formalization
High (0-6 months): | 11 gaps - MFA enforcement, access reviews, TPRM program, vulnerability scanning
Medium (6-12 months): | 7 gaps - Threat intel, communication templates, asset discovery automation
BUDGET ESTIMATE:
Technology (SIEM, vulnerability scanner, MFA): | $450,000
Consulting (TPRM program, IR playbook): | $120,000
Internal Resources (FTE allocation): | 2.5 FTEs for 12 months
RISK EXPOSURE:
Without remediation: | High residual risk in detect/respond functions; regulatory compliance gaps (SOX, PCI DSS)
With remediation: | Maturity level 3.8 positions organization as industry-leading in cybersecurity governance