## RISK REGISTER
Enterprise IT Risk Register
Organization: Sample Enterprise Inc. ¦ Risk Owner: CISO ¦ Date: March 2026 ¦ Assessor: Ayomipo Alademehin, CISA
ID | Risk Category | Risk Description | Threat Source | L | I | Score | Existing Controls | Control Eff. | RL | RI | Residual | Risk Treatment | Status
R001 | Access Control | Unauthorized access to production systems due to weak authentication | External threat actors | 4 | 5 | 20 | Password policy; VPN required | Moderate | 3 | 5 | 15 | Implement MFA for all users | In Progress
R002 | Data Protection | Sensitive customer data exposure via unencrypted databases | Configuration error | 3 | 5 | 15 | Access controls on DB servers | Low | 3 | 4 | 12 | Enable TDE on all customer DBs | Planned
R003 | Third Party | Vendor data breach exposing company information | Supply chain | 4 | 4 | 16 | Vendor contracts with security clauses | Low | 4 | 4 | 16 | Implement TPRM program with annual assessments | Planned
R004 | Malware | Ransomware infection disrupting business operations | Phishing emails | 4 | 5 | 20 | Endpoint AV; email filtering | Moderate | 2 | 5 | 10 | Deploy EDR solution; conduct phishing simulation | In Progress
R005 | Insider Threat | Privileged user misusing access to steal intellectual property | Malicious insider | 2 | 5 | 10 | Background checks; SoD reviews | Moderate | 1 | 5 | 5 | Implement DLP and privileged access monitoring | Completed
R006 | Compliance | Failure to meet SOX ITGC requirements resulting in audit findings | Process gaps | 3 | 4 | 12 | Manual access reviews quarterly | Low | 3 | 3 | 9 | Automate access reviews; formalize change mgmt | In Progress
R007 | Availability | Prolonged system outage due to inadequate disaster recovery | Natural disaster | 2 | 5 | 10 | Daily backups to cloud | Moderate | 2 | 3 | 6 | Test DR plan annually; define RTO/RPO | Planned
R008 | Network Security | Lateral movement after perimeter breach | Advanced persistent threat | 3 | 4 | 12 | Firewall; IDS alerts | Low | 3 | 4 | 12 | Implement network segmentation and zero trust | Planned
R009 | Data Retention | Regulatory penalty for improper data retention | Policy gap | 2 | 3 | 6 | IT retention policy documented | Moderate | 1 | 3 | 3 | Implement automated retention and deletion | Completed
R010 | Patch Management | Exploitation of unpatched critical vulnerabilities | Vulnerability exploit | 4 | 4 | 16 | Monthly patching cycle | Low | 4 | 4 | 16 | Implement risk-based patching (critical within 48h) | In Progress
R011 | Cloud Security | Misconfigured S3 buckets exposing confidential files | Configuration error | 3 | 4 | 12 | Manual bucket reviews | Low | 2 | 4 | 8 | Deploy CSPM tool for continuous monitoring | Planned
R012 | Identity Mgmt | Orphaned accounts used for unauthorized access | Process gap | 3 | 4 | 12 | Quarterly access reviews | Low | 3 | 3 | 9 | Automate deprovisioning; weekly orphan account scans | In Progress
R013 | Physical Security | Unauthorized physical access to data center | Physical intrusion | 2 | 4 | 8 | Badge access; CCTV monitoring | High | 1 | 4 | 4 | Implement mantraps; integrate badge logs with SIEM | Planned
R014 | Mobile Devices | Loss of mobile device containing company data | Device theft/loss | 3 | 3 | 9 | MDM with remote wipe | Moderate | 2 | 3 | 6 | Enforce device encryption; containerization | Completed
R015 | Email Security | Business email compromise (BEC) leading to wire fraud | Social engineering | 3 | 5 | 15 | DMARC/DKIM configured | Low | 3 | 4 | 12 | Implement advanced email threat protection | Planned
Risk Scoring: L (Likelihood) × I (Impact) where 1=Rare/Negligible to 5=Almost Certain/Catastrophic ¦ Critical: 16-25 ¦ High: 12-15 ¦ Medium: 6-11 ¦ Low: 1-5 ¦ Control Effectiveness: High/Moderate/Low